NewYork-Presbyterian/Queens PPS

Project 3.d.ii - Pediatric Asthma Project

*Project Committee Meeting*

*May 10th, 2017 1:00pam – 2:00 pm EST*

**Attendees**: H. Jabbar (NYP/Q), C. Dunkley (NYPQ) , C. Duffy (St. Marys), S. Choudhury (NYPQ), R. Zhu (NYPQ) M. Hay (NYPQ), J. Lavin (MHPWQ), C. Gugliemo (Asthma Coalition ), (NYPQ), A. Simmons (NYPQ) , M. D’Urso (NYPQ), Jennifer (Advanced Pediatrics), G. Sabagol (Advanced Pediatrics ), J. Lavin (MHPWQ), S. Kalinsowki (NYPQ)

| **Topic** | **Discussion** | **Actions** |
| --- | --- | --- |
| 1. **Agenda:** | * Welcome & Purpose * Review & Approve Minutes * Actively Engaged Patient Goals-Mitigation Strategy * Future Deliverables * Rapid Cycle * Questions/Discussions | * N/A |
| 1. **Review Minutes:**   H. Jabbar | * Review and Approved Minutes from 4.12.17 Meeting. | * Meeting minutes were unanimously approved . |
| 1. **Actively Engaged Patient Goals-Mitigation Strategy** 2. Gugliemo | * Update to Actively engaged definition: Any patient that is referred to home care assessment * Include two more columns in the actively engaged templates: Refer to and Home Assessment completion date. In efforts to improve tracking the actively engaged. * Are any providers reporting to other Home Cares than St. Mary’s?   + Claudia will educate any new providers; the PMO can provide the information. * St. Mary’s is closing the loop on completed Home Care Assessments to Dr. Sabagol. * PMO can send weekly provider emails to the partners and Claudia can help with email descriptions and reminders. * Claudia and St. Mary’s can collaborate with PMO on outreach to partners who are not engaged or sending patients. * Claudia and Caroline will coordinate for the conversation on ED patient navigator work. | * New templates were sent out to partners yesterday with updated columns, please reach out to Renjie if there are any questions. * Claudia and St. Mary’s can collaborate with PMO on outreach to partners who are not engaged or sending patients. * S. Choudhury will start the introductions for C. Gugliemo and C. Kean on ED patient navigatior work. |
| 1. **DY3Q4 Deliverables:**   S. Choudhury/  Team | * Metric 5.3 * PMO will develop the Care coordination Roster for reporting including Peds Asthma Center, ED, Saint Mary’s nurses. * The PPS would need to engage pharmacist from the serving areas like Jackson Heights. * A current pharmacy partner is Total Care Rx , in- house pharmacy, and Alexander Infusion. * Create packet for pharmacist from DSRIP to provide to for their patients with laminated visual instructions, educational pamphlet with DSRIP referral information. * Is there a co-pay for Homecare Visit? | * Total Care Rx and Claudia would have a conversation on Asthma education. * C. Duffy will confirm whether Medicaid patients have a co-pay for homecare assessment. |
| 1. **Questions/ Discussion: Team** | * If partners are interested in Cureatr M. Hay can set up notifications with partners to be alerted when patients hit the ED. * Partner would have to submit their patient registry to be uploaded into system. * M. Hay and partners will work on configuring the tool. * H. Jabbar reported out the Education Resource Center is coming to fruition very soon and Nurses are going to be coming to educate patients. * C. Gugliemo and H. Jabbar are reviewing education tools and resources for the Education Resource Center. | * Please contact M. Hay for further information. |